## Sheet1
TC ID | Module | Test Case | Expected Result | Actual Result | Severity | Status | Dev_Status_Comment
TC-HM-01 | Homepage | Hero section loads with banner image | Full-width hero image visible above the fold | Image loads via Cloudinary CDN, renders correctly | Low | Pass
TC-HM-02 | Homepage | Buy / Rent / New Launch tab switcher on hero | Tabs switch intent and update search context | Tabs exist visually; no functional filter context change observed in static render | Medium | Warning
TC-HM-03 | Homepage | Location + BHK search fields submit | Search redirects to filtered listing page | Fields present; JS-driven — functionality not verifiable without live browser session | Medium | Warning
TC-HM-04 | Homepage | Trust indicators display (RERA, 24hr, 3200+ buyers) | Stats are visible and accurate | All three present. '3,200+ buyers advised' is a credibility claim — no source or date | Low | Warning
TC-HM-05 | Homepage | Trending projects carousel | Shows multiple verified live projects | Only 1 unique property shown (Nahar Barberry repeated twice). Carousel is misleading. | High | Fail
TC-HM-06 | Homepage | Builder section populates with logos | 7 builders shown with images | 7 builders shown correctly; images load from Cloudinary | Low | Pass
TC-HM-07 | Homepage | Free consultation CTA — phone link | tel: link triggers dial intent | tel:+919137950050 present and correct | Low | Pass
TC-HM-08 | Homepage | Floating WhatsApp button | Persistent WhatsApp CTA throughout scroll | WA button present with pre-filled message template — working | Low | Pass
TC-HM-09 | Homepage | Homepage contact form — required fields | Name, email, phone required; validation fires | Phone marked required (*), others not. No client-side validation visible in static render | Medium | Warning
TC-HM-10 | Homepage | Popular location links (Bandra, Worli etc.) | Links navigate to filtered results | Links are displayed but lead to no filtered output (Buy page shows zero listings) | High | Fail
TC-BUY-01 | Buy Page | Listings populate on page load | At least one property card visible | 'No listings available in this category right now' — zero inventory | Critical | Fail
TC-BUY-02 | Buy Page | Filter by location | Results narrow to selected area | Filter UI present; no listings to filter against — untestable | Critical | Fail
TC-BUY-03 | Buy Page | Budget range slider (₹50L – ₹3Cr) | Slider adjusts and filters results | Slider UI present; no results to test against | Medium | Warning
TC-BUY-04 | Buy Page | BHK type filter | 1/2/3/4 BHK options narrow listings | Dropdown visible; no data to validate | Medium | Warning
TC-BUY-05 | Buy Page | Sort: Newest / Price Low-High / Price High-Low | URL params change and results re-order | Sort buttons present with correct query params (?sortBy=price_asc etc.) — logic sound | Low | Pass
TC-BUY-06 | Buy Page | Grid vs List view toggle | View switches between card grid and list layout | Links present with /buy and /buy?view=list — correct URL pattern | Low | Pass
TC-BUY-07 | Buy Page | Pagination | Pages 1, 2 … N shown when >N listings | Pagination renders (page 1 shown) despite zero listings — orphaned UI element | Medium | Fail
TC-BUY-08 | Buy Page | Empty state message quality | Clear, actionable empty state with CTA | Generic icon + 'No listings available' with no CTA to contact or explore alternatives | Medium | Fail
TC-RNT-01 | Rent Page | Listings display for rent | Multiple rent listings visible | 4 listings present — functional. But sample data visible ('Editorial Title', 'Title' as property names) | High | Fail
TC-RNT-02 | Rent Page | Listing data integrity | Real property names, locations, prices | 'editorial title' in Wakad at ₹5K, 'Title' in Wakad at ₹50K — clearly test/dummy data still live | High | Fail
TC-RNT-03 | Rent Page | Location accuracy | Properties show correct Mumbai locality | Listings show 'Pune, Mumbai' and 'Wakad, Mumbai' — Wakad is in Pune, not Mumbai. Incorrect. | High | Fail
TC-RNT-04 | Rent Page | Compare checkbox on listing card | Adds property to compare page | Compare link present on each card — URL pattern correct | Low | Pass
TC-RNT-05 | Rent Page | Availability badge ('Available Soon' vs live date) | Dates accurate and current | 'Avail. Jun 2026' shown — plausible but not verifiable. 'Available Soon' without date is vague. | Low | Warning
TC-RNT-06 | Rent Page | Budget range filter (₹10K–₹5L) | Filter narrows listing set correctly | Range is reasonable; UI present | Low | Pass
TC-NL-01 | New Launch | Page loads successfully | HTTP 200, content renders | Server returns internal fetch error (HTTP 500) — page is broken | Critical | Fail
TC-NL-02 | New Launch | New launch listings render | Cards with project images, RERA, possession date | Untestable — page fails to load | Critical | Fail
TC-NL-03 | New Launch | Nav link from header | Navigates to /new-launch | Link exists in nav — but destination is broken | Critical | Fail
TC-BLD-01 | Builders | Builder cards display with image + metadata | Logo, name, est. year, project count, location | All 7 builders render correctly with complete data | Low | Pass
TC-BLD-02 | Builders | Featured + Trending badges | Visual differentiation for featured builders | Both badges present and readable | Low | Pass
TC-BLD-03 | Builders | View Builder deep-link | Navigates to individual builder profile | Links follow pattern /builders/[slug] — correct | Low | Pass
TC-BLD-04 | Builders | Location filter on builders page | Narrows by city/area | Filter UI present; 'All Locations' dropdown visible | Low | Pass
TC-BLD-05 | Builders | Hero carousel (Kanakia featured) | Carousel with prev/next navigation | Chevron navigation present; only Kanakia shown as featured hero — limited data | Low | Warning
TC-EMI-01 | EMI Calculator | Default values load correctly | Sensible pre-filled loan amount, rate, tenure | ₹75L at 8.5% for 20 years — reasonable defaults | Low | Pass
TC-EMI-02 | EMI Calculator | EMI calculation accuracy | Formula: EMI = P*r*(1+r)^n / ((1+r)^n - 1) | Shows ₹65,087/month for ₹75L at 8.5% / 20yr — mathematically correct ✓ | High | Pass
TC-EMI-03 | EMI Calculator | Total interest calculation | Total interest = (EMI × months) − principal | ₹81,20,818 interest on ₹75L — correct | Low | Pass
TC-EMI-04 | EMI Calculator | Amortization schedule — 20 rows for 20 years | Year-by-year breakdown, final balance = ₹0 | 20 rows from 2026–2045; final balance ₹0 — correct | Low | Pass
TC-EMI-05 | EMI Calculator | Interest proportion display | Pie/doughnut shows principal vs interest split | Shows 'Interest 52%' — correct | Low | Pass
TC-EMI-06 | EMI Calculator | Speak to Advisor CTA prefills contact message | URL encodes loan params into contact form message | CTA link includes pre-filled ?message= with loan amount, rate, tenure | Low | Pass
TC-EMI-07 | EMI Calculator | Download report button | Generates downloadable PDF of amortization | Button present — functionality requires JS testing in browser | Medium | Warning
TC-EMI-08 | EMI Calculator | Slider range — loan amount ₹1L to ₹5Cr | Slider moves and recalculates | Range stated — JS-driven, not verifiable statically | Low | Warning
TC-SD-01 | Stamp Duty | Male buyer rate — 6% | Stamp duty = 6% of property value | Shows 6% for male — correct per current Maharashtra rates | Low | Pass
TC-SD-02 | Stamp Duty | Female buyer rate — 5% | 1% concession for women buyers | 5% for female shown — correct | Low | Pass
TC-SD-03 | Stamp Duty | Registration charge | ₹30,000 flat (current IGR rate) | Calculator shows ₹30,000; FAQ page says ₹29,000 — INCONSISTENCY | High | Fail
TC-SD-04 | Stamp Duty | Default property value pre-fill | Reasonable default (e.g. ₹50L) | Default shows ₹5Cr — very high default; may confuse users | Medium | Warning
TC-SD-05 | Stamp Duty | Leave & License tab calculation | 0.25% on stampable amount, ₹1000 reg | Tab present; FAQ describes formula correctly — consistent | Low | Pass
TC-SD-06 | Stamp Duty | Stamp duty info accuracy vs Maharashtra 2024 rates | Rates match IGR Maharashtra published rates | 6% / 5% / 5% joint — consistent with current rates | Low | Pass
TC-BLG-01 | Blog | Blog listing page renders | Grid of articles with image, category, date | 2 articles visible with proper metadata | Low | Pass
TC-BLG-02 | Blog | Category filter tabs | Filters: All, Market Trends, Buying Guide, Legal, Investment, Lifestyle | All 6 category tabs present with correct URL params | Low | Pass
TC-BLG-03 | Blog | Blog inventory depth | 10+ articles for a credible knowledge hub | Only 2 articles total — very thin content; '1 min read' suggests stubs | High | Fail
TC-BLG-04 | Blog | Newsletter subscribe form | Email field + submit, confirmation fee | Form elements present | Low | Pass